## Version
OrangeHRM Regression
Release: | 2025-12-31
Date | Version | Author | Comments
2026-02-25 | 1.0 | Lucas Alexandre | Lorem Ipsum
Call outs & Exceptions
Index | Comments
1 | URL: http://localhost:8080/web/index.php/auth/login
2
3
4
5
6

## Timeline
App | Code Drop Date | PROD Release Date | N° of Availiable Test Days | Contagem de Test Scenario | Rótulos de Coluna |  |  |  | Priority Test Cases | Total per Day
OrangeHRM | 2026-02-16 | 2026-03-06 | 15 | Rótulos de Linha | High | Low | Medium | Total Geral | High | 0.86667
Database | 2026-02-14 | 2026-03-06 | 15 | Custom Fields | 1 |  | 6 | 7 | Medium | 0.4
Midleware | 2026-02-16 | 2026-03-06 | 15 | Data Import | 4 |  |  | 4 | Low | 0.26667
|  |  |  | Employee List | 5 |  |  | 5 | Total | 1.5333
|  |  |  | Optional Fields |  | 4 |  | 4
|  |  |  | Reports | 3 |  |  | 3
|  |  |  | Total Geral | 13 | 4 | 6 | 23
Formulas:
N° of Availiable Test Days = NETWORKDAYS([Code Drop Date],[PROD Release Date])

## Risk
Risk | Mitigation Plan | Plan Status | Note
Due to amount of defects SQaR is on risk of deliver the test cases for this release | Prioritization of test cases is done with Bussiness team and planned Weekend Work; If requried Release Date may also change; We are working on a bridge with Dev team to get faster response on defect closure; | Approved | LC 11/05] Prioritization done in X test management tool

## Q&A
Date | Type | Status | Priority | Pending With | Question | Answer
2026-02-05 | Access | Closed | High | Lucas | Who can provide us DB access? | Ticket requried for install Dbeaver and Dev team will provide connection details
2026-02-05 | Requirement | In Review | High | Lucas | What error messag should be display for CSV when system check and get some empty or invalid data on the file? | Bussiness team is checking what should be the error message
2026-02-05 | Info | Closed | Medium | Lucas | Where should Reporting methods appear? | Moved to a new release - TBD
2026-02-05 | Info | Closed | Medium | Lucas | Where should Termination reasons appear? | Moved to a new release - TBD

## Features
Jira Type | ID | In Scope | Notes
Capability | CAP-1 | Yes | Added PIM page functions
Feature | FT-1 | Yes | Added PIM page functions
Story | ST-1 | Yes | Added PIM page functions

## High Test Design V1.0
Capability | App | Test Scenario | Requisite | Validation Checkpoints | TC Count | Test Type | Run Type | Priority | Review Status | Notes
CAP-01 | OrangeHRM | TC01_Verify if after creating a employee with login details and set Status as Enabled, then system allow user to login | Access to OrangeHRM User with Admin profile Valid data for new employee creation | Verify user should be able to access the system with a Admin account and see Admin and PIM menu options; Go to PIM > Employee List and click on Add button then create a new employee with login credentials as well with Status as enabled successfully; Search the new employee on PIM > Employee List; Login successfully using the new employee credentials New user shouldn't be able to see Admin and PIM menu options; Verify hs_hr_employee table and check if saved details are correct; Verify ohrm_user table and check if saved details are correct; | 1 | E2E | Automation | High | Approved | LC 09/02/26] May become part of regression test case
CAP-01 | OrangeHRM | TC02_Verify if after creating a employee with login details and set Status as Disabled, then system shouldn't allow user to login | Access to OrangeHRM User with Admin profile Valid data for new employee creation | Verify user should be able to access the system with a Admin account and see Admin and PIM menu options; Go to PIM > Employee List and click on Add button then create a new employee with login credentials as well with Status as enabled successfully; Search the new employee on PIM > Employee List; Verify user shouldn't be able to login using the new employee credentials; Verify hs_hr_employee table and check if saved details are correct; Verify ohrm_user table and check if saved details are correct; | 1 | E2E | Automation | High | Approved | LC 09/02/26] May become part of regression test case
CAP-01 | OrangeHRM | TC03_Verify system allow to create a new employee | Access to OrangeHRM User with Admin profile Valid data for new employee creation | Verify user should be able to access the system with a Admin account and see Admin and PIM menu options; Go to PIM > Employee List and click on Add button then create a new employee; Search the new employee on PIM > Employee List; Verify hs_hr_employee table and check if saved details are correct; | 1 | Smoke | Automation | High | Approved
CAP-01 | OrangeHRM | TC04_Verify Admin user can update a employee register and save new contact details successfully | Access to OrangeHRM User with Admin profile Availiable employee register | Verify user should be able to access the system with a Admin account and see Admin and PIM menu options; Go to PIM > Employee List and click on Edit button at desired employee register; Search the new employee on PIM > Employee List; Verify hs_hr_employee table and check if saved details are correct; | 1 | E2E | Automation | High | Approved | LC 09/02/26] May become part of regression test case
CAP-01 | OrangeHRM | TC05_Verify Admin user can remove a employee register successfully | Access to OrangeHRM User with Admin profile Availiable employee register | Verify user should be able to access the system with a Admin account and see Admin and PIM menu options; Go to PIM > Employee List and click on Remove button at desired employee register; Search the new employee on PIM > Employee List and check it will not be visible anymore; Verify deleted user is not able to login; Verify hs_hr_employee table and check if details are removed; Verify ohrm_user table table and check if details are removed; | 1 | E2E | Automation | High | Approved | LC 09/02/26] May become part of regression test case
CAP-01 | OrangeHRM | TC06_Verify Admin user can Activate and Deactivate Optional Fields and system should allow Admin user to update the Optional fields on a employee register successfully | Access to OrangeHRM User with Admin profile Availiable employee register | Verify user should be able to access the system with a Admin account and see Admin and PIM menu options; Go to PIM > Configuration > Optional Fields; Activate the desired optional fields and click on Save; Verify when updating a employee register at employee personal details page that activated Optional Fields should be presented; Update the Optional fields with correct data and save successfully; Verify hs_hr_employee table and check if details are saved; | 4 | E2E | Manual | Low | Approved | LC 09/02/26] Need to test with below conditions: - 1 Deprecated Fields - 1 Country Specific Information - 1 Deprecated Fields & 1 Country Specific Information - All fields (Deprecated & Country Specific Information): Marked as N/A since is redundant
CAP-01 | OrangeHRM | TC07_Verify Admin user can create a Custom Fields and system should allow Admin user to update the new Custom fields on a employee register successfully | Access to OrangeHRM User with Admin profile Availiable employee register | Verify user should be able to access the system with a Admin account and see Admin and PIM menu options; Go to PIM > Configuration > Custom Fields and click on +Add button; Fill the Field Name, Screen and Type inputs with the desired data and click on Save; Verify when updating a employee register at employee personal details page that activated Optional Fields should be presented; Update the Optional fields with correct data and save successfully; Verify hs_hr_employee table and check if details are saved; | 2 | E2E | Automation | Medium | Approved | LC 09/02/26] Need to test with below conditions: - 1 Text or Number Custom Field - 1 Drop Down Custom Field LC 09/02/26] Add only on the Personal Details
CAP-01 | OrangeHRM | TC08_Verify Admin user can update a Custom Fields successfully and previous data on the employee register shouldn't be affecte by the update | Access to OrangeHRM User with Admin profile Availiable employee register Availiable custom field | Verify user should be able to access the system with a Admin account and see Admin and PIM menu options; Go to PIM > Configuration > Custom Fields and click on edit at desired custom field register; Update the Field Name and Screen input with the desired data and click on Save; Verify at employee details page that activated Optional Fields should be presented and with updated name; Verify hs_hr_employee table and check if details are updated; | 2 | E2E | Automation | Medium | Approved | LC 09/02/26] Need to test with below conditions: - 1 Text or Number Custom Field - 1 Drop Down Custom Field LC 09/02/26] Add only on the Personal Details
CAP-01 | OrangeHRM | TC09_Verify Admin user can delete a Custom Fields successfully and previous data on the employee register should be deleted as well | Access to OrangeHRM User with Admin profile Availiable employee register Availiable custom field | Verify user should be able to access the system with a Admin account and see Admin and PIM menu options; Go to PIM > Configuration > Custom Fields and click on Remove at desired custom field register; Confirm the removal of the Custom Field on the modal successfully; Verify at employee details page that activated Optional Fields shouldn't be presented; Verify hs_hr_employee table and check if details are removed; | 2 | E2E | Automation | Medium | Approved | LC 09/02/26] Need to test with below conditions: - 1 Text or Number Custom Field - 1 Drop Down Custom Field LC 09/02/26] Add only on the Personal Details
CAP-01 | OrangeHRM | TC10_Verify Admin user can update a Custom Fields successfully form Text or Number to Drop Down and previous data on the employee register shouldn't be affecte by the update? | Access to OrangeHRM User with Admin profile Availiable employee register Availiable custom field | Verify user should be able to access the system with a Admin account and see Admin and PIM menu options; Go to PIM > Configuration > Custom Fields and click on edit at desired custom field register; Update the Field Name and Type input with the desired data and click on Save; Verify at employee details page that activated Optional Fields should be presented and with updated name; Verify hs_hr_employee table and check if details are saved; | 1 | Exploratory | Manual | High | Approved | LC 09/02/26] Bussiness is not aware how the system should behave then we will proceed with test execution for this TC sharing the results to Bussiness and Dev team LC 17/02/26] Confirmed with Dev and Bussiness and details shouldn't be deleted as the only thing that should be affected is the inputs presented on front end. Marking this Test case as N/A since we already validate in previous test cases;
CAP-01 | OrangeHRM | TC11_Verify Admin user can create a Report successfully | Access to OrangeHRM User with Admin profile Availiable employee register | Verify user should be able to access the system with a Admin account and see Admin and PIM menu options; Go to PIM > Reports and click on +Add button; Fill the Report Name Input, add a selection criteria and Display Fields and click on Save; Click on view report and check if details are presented succeessfully based on the provided criteria and display fields; Verify ohrm_report table and check if details are saved; Verify ohrm_selected_group_field table and check if details are saved; Verify ohrm_selected_filter_field table and check if details are saved; Verify ohrm_report_group table and check if details are saved; Verify ohrm_selected_display_field table and check if details are saved; Verify ohrm_selected_composite_display_field table and check if details are saved; Verify ohrm_selected_display_field_group table and check if details are saved; | 1 | E2E | Automation | High | Approved | LC 09/02/2026] Financial Team flag this Test Case as Critical for test as reports are critical for clients
CAP-01 | OrangeHRM | TC12_Verify Admin user can edit a Report successfully | Access to OrangeHRM User with Admin profile Availiable employee register Availiable Report register | Verify user should be able to access the system with a Admin account and see Admin and PIM menu options; Go to PIM > Reports and click on Edit button at desired Report; Update the Report Name Input, Selection Criteria and Display Fields and click on Save; Click on view report and check if details are presented succeessfully based on the provided criteria and display fields; Verify ohrm_report table and check if details are saved; Verify ohrm_selected_group_field table and check if details are updated; Verify ohrm_selected_filter_field table and check if details are updated; Verify ohrm_report_group table and check if details are updated; Verify ohrm_selected_display_field table and check if details are updated; Verify ohrm_selected_composite_display_field table and check if details are updated; Verify ohrm_selected_display_field_group table and check if details are updated; | 1 | E2E | Automation | High | Approved | LC 09/02/2026] Financial Team flag this Test Case as Critical for test as reports are critical for clients
CAP-01 | OrangeHRM | TC13_Verify Admin user can delete a Report successfully | Access to OrangeHRM User with Admin profile Availiable employee register Availiable Report register | Verify user should be able to access the system with a Admin account and see Admin and PIM menu options; Go to PIM > Reports and click on Edit button at desired Report; Click on delete report and check if the same will not be visible at report search; Verify ohrm_report table and check if details are deleted; Verify ohrm_selected_group_field table and check if details are deleted; Verify ohrm_selected_filter_field table and check if details are deleted; Verify ohrm_report_group table and check if details are deleted; Verify ohrm_selected_display_field table and check if details are deleted; Verify ohrm_selected_composite_display_field table and check if details are deleted; Verify ohrm_selected_display_field_group table and check if details are deleted; | 1 | E2E | Automation | High | Approved | LC 09/02/2026] Financial Team flag this Test Case as Critical for test as reports are critical for clients
CAP-01 | OrangeHRM | TC14_Verify Admin user can upload a csv file to import new employee register successfully | Access to OrangeHRM User with Admin profile | Verify user should be able to access the system with a Admin account and see Admin and PIM menu options; Go to PIM > Configurations > Data import and click on Download Sample CSV file; Fill the csv file with valid data and save successfully; Click on Select File and add the CSV file then click on Upload; Check success message; Verify hs_hr_employee table and check if details are saved; Search employee at PIM > Employee List and check that teh register is uploaded succssfully on the system | 1 | E2E | Automation | High | Approved
CAP-01 | OrangeHRM | TC15_Verify if Admin user upload a csv file with missing first name/last name for new employee register then system present a error message | Access to OrangeHRM User with Admin profile | Verify user should be able to access the system with a Admin account and see Admin and PIM menu options; Go to PIM > Configurations > Data import and click on Download Sample CSV file; Fill the csv file with invalid data and save successfully; Click on Select File and add the CSV file then click on Upload; Check error message; Verify hs_hr_employee table and check if details are not saved; Search employee at PIM > Employee List and check that the register is not uploaded on the system | 1 | E2E | Manual | High | Approved | LC 09/02/2026] Use more then 1 data on the csv and randomly add or remove the requried fields for each record
CAP-01 | OrangeHRM | TC16_Verify if Admin user upload a csv file with invalid date type format on new employee register then system present a error message | Access to OrangeHRM User with Admin profile | Verify user should be able to access the system with a Admin account and see Admin and PIM menu options; Go to PIM > Configurations > Data import and click on Download Sample CSV file; Fill the csv file with invalid data and save successfully; Click on Select File and add the CSV file then click on Upload; Check error message; Verify hs_hr_employee table and check if details are not saved; Search employee at PIM > Employee List and check that the register is not uploaded on the system | 1 | E2E | Manual | High | Approved | LC 09/02/2026] Use more then 1 data on the csv and randomly add or remove the correct date formatt for each record
CAP-01 | OrangeHRM | TC17_Verify if Admin user upload a csv file with invalid gender value on new employee register then system present a error message | Access to OrangeHRM User with Admin profile | Verify user should be able to access the system with a Admin account and see Admin and PIM menu options; Go to PIM > Configurations > Data import and click on Download Sample CSV file; Fill the csv file with invalid data and save successfully; Click on Select File and add the CSV file then click on Upload; Check error message; Verify hs_hr_employee table and check if details are not saved; Search employee at PIM > Employee List and check that the register is not uploaded on the system | 1 | E2E | Manual | High | Approved | LC 09/02/2026] Use more then 1 data on the csv and randomly add or remove the correct sex gender for each record
CAP-01 | OrangeHRM | TC18_Verify if Admin user upload a csv file with invalid Nationality value on new employee register then system present a error message | Access to OrangeHRM User with Admin profile | Verify user should be able to access the system with a Admin account and see Admin and PIM menu options; Go to PIM > Configurations > Data import and click on Download Sample CSV file; Fill the csv file with invalid data and save successfully; Click on Select File and add the CSV file then click on Upload; Check error message; Verify hs_hr_employee table and check if details are not saved; Search employee at PIM > Employee List and check that the register is not uploaded on the system | 1 | E2E | Manual | High | Approved | LC 09/02/2026] Use more then 1 data on the csv and randomly add or remove the correct sex gender for each record
CAP-01 | OrangeHRM | TC19_Verify if Admin user upload a csv file with invalid Matrial Status value on new employee register then system present a error message | Access to OrangeHRM User with Admin profile | Verify user should be able to access the system with a Admin account and see Admin and PIM menu options; Go to PIM > Configurations > Data import and click on Download Sample CSV file; Fill the csv file with invalid data and save successfully; Click on Select File and add the CSV file then click on Upload; Check error message; Verify hs_hr_employee table and check if details are not saved; Search employee at PIM > Employee List and check that the register is not uploaded on the system | 1 | E2E | Manual | High | Approved | LC 09/02/2026] Use more then 1 data on the csv and randomly add or remove the correct sex gender for each record

## Low Test Design V1.0
App | Flow | Priority | Test Scenario | Status | Run Type | Notes
OrangeHRM | Employee List | High | TC01_Verify if after creating a employee with login details and set Status as Enabled, then system allow user to login | Not Started | Automation
OrangeHRM | Employee List | High | TC02_Verify if after creating a employee with login details and set Status as Disabled, then system shouldn't allow user to login | Not Started | Automation
OrangeHRM | Employee List | High | TC03_Verify system allow to create a new employee | Not Started | Automation
OrangeHRM | Employee List | High | TC04_Verify Admin user can update a employee register and save new contact details successfully | Not Started | Automation
OrangeHRM | Employee List | High | TC05_Verify Admin user can remove a employee register successfully | Not Started | Automation
OrangeHRM | Optional Fields | Low | TC06_1 Deprecated Field_Verify Admin user can Activate and Deactivate Optional Fields and system should allow Admin user to update the Optional fields on a employee register successfully | Passed | Manual
OrangeHRM | Optional Fields | Low | TC07_1 Country Specific Information_Verify Admin user can Activate and Deactivate Optional Fields and system should allow Admin user to update the Optional fields on a employee register successfully | Passed | Manual
OrangeHRM | Optional Fields | Low | TC08_1 Deprecated Fields & 1 Country Specific Information_Verify Admin user can Activate and Deactivate Optional Fields and system should allow Admin user to update the Optional fields on a employee register successfully | Passed | Manual
OrangeHRM | Optional Fields | Low | TC09_All fields (Deprecated & Country Specific Information)_Verify Admin user can Activate and Deactivate Optional Fields and system should allow Admin user to update the Optional fields on a employee register successfully | N/A | Manual
OrangeHRM | Custom Fields | Medium | TC10_Text or Number Custom Field_Verify Admin user can create a Custom Fields and system should allow Admin user to update the new Custom fields on a employee register successfully | Not Started | Automation
OrangeHRM | Custom Fields | Medium | TC11_Drop Down Custom Field_Verify Admin user can create a Custom Fields and system should allow Admin user to update the new Custom fields on a employee register successfully | Not Started | Automation
OrangeHRM | Custom Fields | Medium | TC12_Text orNumber Custom Field_Verify Admin user can update a Custom Fields successfully and previous data on the employee register shouldn't be affecte by the update | Not Started | Automation
OrangeHRM | Custom Fields | Medium | TC13_Drop Down Custom Field_Verify Admin user can update a Custom Fields successfully and previous data on the employee register shouldn't be affecte by the update | Not Started | Automation
OrangeHRM | Custom Fields | Medium | TC14_Text or Number Custom Fields_Verify Admin user can delete a Custom Fields successfully and previous data on the employee register should be deleted as well | Not Started | Automation
OrangeHRM | Custom Fields | Medium | TC15_Drop Down Custom Fields_Verify Admin user can delete a Custom Fields successfully and previous data on the employee register should be deleted as well | Not Started | Automation
OrangeHRM | Custom Fields | High | TC16_Verify Admin user can update a Custom Fields successfully form Text or Number to Drop Down and previous data on the employee register shouldn't be affecte by the update? | N/A | Manual
OrangeHRM | Reports | High | TC17_Verify Admin user can create a Report successfully | Not Started | Automation
OrangeHRM | Reports | High | TC18_Verify Admin user can edit a Report successfully | Not Started | Automation
OrangeHRM | Reports | High | TC19_Verify Admin user can delete a Report successfully | Not Started | Automation
OrangeHRM | Data Import | High | TC20_Verify Admin user can upload a csv file to import new employee register successfully | Failed | Automation | Import is failing and the error message is not friendly user
OrangeHRM | Data Import | High | TC21_Verify if Admin user upload a csv file with missing first name/last name for new employee register then system present a error message | Failed | Manual | Import is failing and the error message is not friendly user
OrangeHRM | Data Import | High | TC22_Verify if Admin user upload a csv file with invalid date type format on new employee register then system present a error message | Failed | Manual | Import is failing and the error message is not friendly user
OrangeHRM | Data Import | High | TC23_Verify if Admin user upload a csv file with invalid gender value on new employee register then system present a error message | Failed | Manual | Import is failing and the error message is not friendly user
OrangeHRM | Data Import | High | TC24_Verify if Admin user upload a csv file with invalid Nationality value on new employee register then system present a error message | Failed | Manual | Import is failing and the error message is not friendly user
OrangeHRM | Data Import | High | TC25_Verify if Admin user upload a csv file with invalid Marital Status value on new employee register then system present a error message | Failed | Manual | Import is failing and the error message is not friendly user

## Impacted Apps
Dev component | Impacted | Code Drop Date | Dev POC | Notes
OrangeHRM | Yes
OrangeHRM Database | Yes
Middleware | Yes

## Brainstorm Flow
Page | Functions | Flows | User Type | Login Access | Active User
PIM | Employee List | Add | SSE | Yes | Yes
| Reports | Remove | ADMIN | No | No
| Optional Fields | Update
Custom Fields
Data Import
Reporting Methods
Termination Reasons

## Legends
Test Type | Run Type | Priority | Question Type | Scope / Impact | Jira Type | Review / Risk Status
E2E | Manual | High | Access | Yes | Capability | Approved
Smoke | Automation | Medium | Requirement | No | Feature | Reproved
Regression |  | Low | Scope | NA | Story | Not Applicable
Accesibility |  |  | Info
Performance
Stress
Load
Exploratory